## Overview
Data Quality Project - Updated Roadmap v2
GMP+ International ¦ Reference date: 2 April 2026 ¦ PM: Mirella van der Kleij ¦ Sponsor: Martin van den Bedum ¦ Budget: €325K (incl. €30K tolerance)
PROJECT STATUS SUMMARY
| 1/5 | 1/5 | 3/5 | ~8 wks
| Phases completed | In progress (delayed) | Not started | Delay vs plan
# | Phase | Original | Rescheduled | Status | Notes
1 | Preparation | Nov 2025 | Nov 2025 | COMPLETED | Team, governance, resources, Data Vision first phase. Completed on schedule.
2 | Deep Dive | Dec 2025 - Mar 2026 | Jan 2026 - Apr 2026 | IN PROGRESS | Approx. 8 weeks delayed. Incl. Data Analysis on BR/Contacts. Backlog and SME interviews not yet fully completed.
3 | Keep Core Clean | Feb - Mar 2026 | Apr - May 2026 | NOT STARTED | Quick wins. Platform architecture analysis (TRIMM, 4 weeks). 1,700+ field analysis (Kasper) is one component. Clean up or start afresh?
4 | Data Entry | Mar - Apr 2026 | May - Jun 2026 | NOT STARTED | Validation rules, smart dropdowns, standard formats. Merged with Data Cleaning.
5 | Data Cleaning | Apr - Jun 2026 | Jun - Aug 2026 | NOT STARTED | Business-critical data cleaning, monitoring dashboard, Phase 1 evaluation.
GO/NO-GO DECISIONS & MILESTONES
# | Milestone | Original | Rescheduled | Type | Notes
1 | Go/No-Go #1 (after Deep Dive) | Jan 2026 | Apr 2026 | Decision point | Data Vision approved, Data Strategy accepted, Backlog prioritised.
2 | Platform Decision | Mar 2026 | Q2 2026 (flexible) | Splitpoint | Platform architecture analysis (TRIMM) is key dependency. 1,700+ field analysis (Kasper) is one component. Architecture blueprint, systems deep dive, roadmap.
3 | Leadership transition | - | 1 Apr 2026 | Organisation | Martin becomes Transformation Manager, continues to lead project with Mirella.
4 | Go/No-Go #2 (after Data Entry) | Apr 2026 | Jun 2026 | Decision point | Validation rules live, data entry errors reduced, data management protocol implemented.
5 | Phase 1 Evaluation | Jun 2026 | Aug 2026 | Final evaluation | Data accuracy measurement, duplicate reduction, CB feedback, Phase 2 recommendation.
KEY DEPENDENCIES
# | Dependency | Description |  | Timing
1 | Platform Decision | D365 CE optimise, different supplier, or migrate? Platform architecture analysis (TRIMM) is the key dependency. 1,700+ field analysis (Kasper Dokter) is one component. Risk analysis required. |  | Q2 2026 (flexible)
2 | Supplier selection | Which external IT supplier(s) for implementation? Not yet determined; dependent on platform decision. |  | After platform decision
QUICK WINS (from use cases)
# | Quick Win | Source Use Case | Impact | Effort | Phase
1 | Make Country field mandatory for Accounts | Account DQ | High - stops "we don't know where accounts are" | Low | Keep Core Clean
2 | Activate duplicate detection at CB entry | Account DQ | High - prevents duplicate companies | Medium | Keep Core Clean
3 | First data quality dashboard (duplicates, missing fields) | CB Performance | High - makes quality issues visible | Medium | Keep Core Clean
4 | Redefine Account Type dropdown | Account DQ | Medium - better categorisation | Low | Data Entry
5 | Legal Business Registration validation (EU plug-in) | Account DQ | High - European data standard | Medium | Data Entry
6 | Remove redundant fields (Certification Body, Company Relation on Account) | Account DQ | Medium - less confusion, cleaner form | Low | Keep Core Clean

## Gantt Timeline
Data Quality Project - Gantt Timeline v2 (Reference date: 2 April 2026)
Coloured cells = activity. Grey cells = future (not yet started). Update periods and provide to Rick to regenerate the HTML.
Activity / Phase | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Complete Deep Dive (incl. BR/Contacts) | Mar: Mar - Apr
incl. Data Analysis BR/Contacts | bar: Mar
Go/No-Go #1 | Apr: >>> MILESTONE
Keep Core Clean + Quick Wins | Apr: Apr - May
Platform Decision (Q2) | Apr: Q2 (flexible)
Data Entry + Data Cleaning | May: May - Aug
Go/No-Go #2 | Jun: >>> MILESTONE
Phase 1 Evaluation | Aug: >>> MILESTONE
TRIMM engagement (orig.) | Mar: through May (orig.)
TRIMM extension? | May: Extension?
IF migration: new platform | Jun: POC + Migration (Q3-Q4)
Platform architecture analysis (TRIMM, 4 wk) | Apr: Apr - Jun
LEGEND
Orange | Mar: Active/delayed phase
Purple | Mar: Planned phase (started)
Light purple | Mar: Planned phase (future)
Green | Mar: Final phase
Grey | Mar: Not yet started / future
Striped | Mar: Conditional migration track
>>> MILESTONE | Mar: Decision point

## Retrospective
Retrospective: What has been delivered? (Nov 2025 - Apr 2026)
# | Deliverable / Activity | Status | Phase | Owner
1 | Project team formed | Done | Preparation | Mirella
2 | Governance structure established | Done | Preparation | Martin
3 | Resources allocated | Done | Preparation
4 | TRIMM contracted and started | Done | Preparation | Arnold / Jeroen
5 | Data Vision first phase completed | Done | Preparation
6 | Data Vision reviewed and annotated | Done | Deep Dive | Team
7 | TRIMM Data Strategy v0.1 delivered and critically reviewed | Done | Deep Dive | Team
8 | TRIMM Data Strategy v0.2 assessed | Done | Deep Dive | Team
9 | TRIMM Data Strategy v0.3 delivered (significantly improved) | Done | Deep Dive | TRIMM
10 | Data Vision latest draft 10 Mar 2026 | Done | Deep Dive | Team
11 | 5 Use cases developed | Done | Deep Dive | Team
12 | Medallion Architecture analysis (current vs future state) | Done | Deep Dive | Rick
13 | Key processes mapped | Done | Deep Dive | Team
14 | Process prioritisation completed | Done | Deep Dive | Mirella, Martin, Stan, Rick, Ellen
15 | Data Vision approved by MT - final | Done | Deep Dive | Mirella
16 | Project roadmap/timeline completed | Done | Deep Dive | Rick + Mirella
17 | Data Strategy final approval by MT - 15 April | In progress | Deep Dive | Mirella
18 | Data Analysis Business Requests & Contacts | In progress | Deep Dive | Team
19 | Backlog and prioritisation formalisation | In progress | Deep Dive | Mirella + Rick
20 | SME interviews completion | In progress | Deep Dive | Team

## Forward Plan
Forward Plan v2: Rescheduled phases (Apr 2026 - Aug 2026)
# | Phase | Deliverable | Period | Owner
1 | Complete Deep Dive | Formalise and prioritise backlog | Mar - Apr 2026 | Mirella + Rick
2 | Complete Deep Dive | Data Analysis on BR / Contacts | Mar - Apr 2026 | Team
3 | Complete Deep Dive | Complete remaining SME interviews | Mar - Apr 2026 | Team
4 | Complete Deep Dive | Data Strategy final approval by MT - 15 April | Mar - Apr 2026 | Mirella
5 | Complete Deep Dive | Discuss "Market Development" pillar | Mar - Apr 2026 | Project team
6 | Keep Core Clean + Quick Wins | Quick Win: Country field mandatory | Apr - May 2026 | Rick
7 | Keep Core Clean + Quick Wins | Quick Win: Duplicate detection at CB entry | Apr - May 2026 | Rick
8 | Keep Core Clean + Quick Wins | Quick Win: First DQ dashboard | Apr - May 2026 | Rick + TRIMM
9 | Keep Core Clean + Quick Wins | Quick Win: Remove redundant Account fields | Apr - May 2026 | Team
10 | Keep Core Clean + Quick Wins | Data management protocol | Apr - May 2026 | Mirella + TRIMM
11 | Keep Core Clean + Quick Wins | Platform architecture analysis (key dependency for next steps; field analysis Kasper is one component) | Apr - May 2026 | Rick + Martin
12 | Keep Core Clean + Quick Wins | Architecture analysis: blueprint, systems deep dive (POC + suppliers), roadmap (4 weeks) | Apr - May 2026 | TRIMM + Rick + Martin
13 | Keep Core Clean + Quick Wins | Identify essential vs redundant data | Apr - May 2026 | Team
14 | Keep Core Clean (Track B) | POC with selected platform | Apr - May 2026 | Team + ext. Vendor
15 | Keep Core Clean (Track B) | Data mapping current to new platform | Apr - May 2026 | Rick
16 | Keep Core Clean (Track B) | Define data quality rules for new platform | Apr - May 2026 | TRIMM + Team
17 | Keep Core Clean (Track B) | CB communication plan for platform switch | Apr - May 2026 | Mirella
18 | Data Entry + Data Cleaning | Implement validation rules per use case | May - Aug 2026 | Supplier
19 | Data Entry + Data Cleaning | Smart dropdowns and controlled picklists | May - Aug 2026 | Rick + Ellen
20 | Data Entry + Data Cleaning | Quick Win: Redefine Account Type dropdown | May - Aug 2026 | Rick + Ellen
21 | Data Entry + Data Cleaning | Quick Win: Legal Business Registration validation (EU plug-in) | May - Aug 2026 | Supplier
22 | Data Entry + Data Cleaning | Business-critical data cleaning per backlog priority | May - Aug 2026 | Team + SMEs
23 | Data Entry + Data Cleaning | Automated cleaning (AI/scripts) | May - Aug 2026 | Rick
24 | Data Entry + Data Cleaning | CB Performance Dashboard live (Power BI) | May - Aug 2026 | Rick + TRIMM
25 | Data Entry + Data Cleaning | Data quality monitoring dashboard | May - Aug 2026 | Rick
26 | Data Entry + Data Cleaning | Phase 1 evaluation and Phase 2 recommendations | May - Aug 2026 | Mirella + Team
27 | Data Entry + Data Cleaning | Data Governance Framework — domain-specific quality norms, measurement methods and escalation paths | May - Aug 2026 | Rick + Martin
GO/NO-GO & EVALUATION CRITERIA
28 | Go/No-Go #1 criteria | Data Vision approved by MT | Apr 2026
29 | Go/No-Go #1 criteria | Roadmap/timeline completed | Apr 2026
30 | Go/No-Go #1 criteria | Data Strategy v0.3+ accepted as working document | Apr 2026
31 | Go/No-Go #1 criteria | Backlog prioritised with business impact scoring | Apr 2026
32 | Go/No-Go #2 criteria | Validation rules live for top 3 use cases | Jun 2026
33 | Go/No-Go #2 criteria | Measurable reduction in data entry errors | Jun 2026
34 | Go/No-Go #2 criteria | Data management protocol implemented | Jun 2026
35 | Go/No-Go #2 criteria | Platform risk analysis completed | Jun 2026
36 | Final evaluation criteria | Data accuracy measurement (baseline vs current) | Aug 2026
37 | Final evaluation criteria | Duplicate percentage reduced | Aug 2026
38 | Final evaluation criteria | SME and CB feedback on data quality improvement | Aug 2026
39 | Final evaluation criteria | Recommendation for Phase 2 scope and budget | Aug 2026

## Team & Risks
Project Team, SMEs & Risks
PROJECT TEAM
# | Name | Role | Notes
1 | Mirella van der Kleij | Project Manager
2 | Martin van den Bedum | Sponsor / Project Governance | Becomes Transformation Manager from 1 Apr 2026; continues to lead project
3 | Rick van Dijk | Project Member
4 | Stan Hendriks | Project Member
5 | Ellen van Dorssen | Project Member
SUBJECT MATTER EXPERTS (SMEs)
# | Name | Role | Domain
1 | Ellen van Dorssen | SME | D365 CE / Resco / Audit
2 | Dalia Brkulic | SME | Monitoring database
3 | Wenxin Guo | SME | Helpdesk
4 | Olyn San Miguel | SME | Business Development
5 | Astrid Straub | SME | Administrative
EXTERNAL PARTNERS
| TRIMM | Arnold Maskat, Jeroen Wijnholds | BI / Data Strategy consultancy, 16 hrs/week
Involvement of other IT suppliers to be determined after the platform decision.
RISKS & POINTS OF ATTENTION
# | Risk | Severity | Notes
1 | Platform decision delay | High | Cascade effect on all phases. Platform architecture analysis (TRIMM) is key dependency; field analysis by Kasper is one component.
2 | Supplier selection/availability | High | Which IT supplier(s)? Not yet determined. May delay implementation.
3 | TRIMM engagement end | Medium | Engagement ends ~May 2026. Extension not yet discussed.
4 | Budget monitoring | Medium | Budget €325K incl. €30K tolerance.
5 | SME availability | Medium | SMEs have day-to-day responsibilities alongside the project.